## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US01 | Register account | As a TA applicant I want to register an account So that I can use the recruitment system. | Must | 1 | 1. Required fields must be completed before registration is accepted. 2. The system must reject a duplicate student number or email address. 3. A successful registration must be saved to the data file and confirmed to the user. | 3 | Epic: Applicant onboarding | 2026-03-09 | 2026-03-22
US02 | Log in and log out | As a user I want to log in and log out So that my actions are associated with my account securely. | Must | 1 | 1. Valid credentials must allow the user to log in. 2. Invalid credentials must show a clear error message. 3. Logging out must end the session and return the user to the login screen. | 3 | Epic: Applicant onboarding | 2026-03-09 | 2026-03-22
US03 | Maintain applicant profile | As a TA applicant I want to create and edit my profile So that Module Organisers can review my background. | Must | 1 | 1. The user must be able to save name, programme, year, and contact details. 2. Required fields must be validated before saving. 3. Saved profile data must be loaded correctly when the user opens the profile again. | 5 | Epic: Applicant onboarding | 2026-03-09 | 2026-03-22
US04 | Upload CV | As a TA applicant I want to upload my CV So that my application includes supporting evidence. | Must | 1 | 1. The system must allow the user to select a CV file in the supported format. 2. If no file is selected, the user must see a clear prompt. 3. The file path or file reference must be stored with the applicant record. | 3 | Epic: Applicant onboarding | 2026-03-09 | 2026-03-22
US05 | Record skills and availability | As a TA applicant I want to record my skills and availability So that jobs can be matched to my capability and schedule. | Should | 2 | 1. The user must be able to enter and update skill tags. 2. The user must be able to save availability information. 3. The saved information must remain available when the profile is reopened. | 3 | Epic: Applicant onboarding | 2026-03-23 | 2026-04-12
US06 | Browse open jobs | As a TA applicant I want to browse available jobs So that I can find suitable opportunities. | Must | 1 | 1. The job list must show open jobs only. 2. Each listed job must display key summary information such as title, module, and deadline. 3. If there are no open jobs, the system must show an appropriate message. | 3 | Epic: Job discovery | 2026-03-09 | 2026-03-22
US07 | View job details | As a TA applicant I want to view the details of a job So that I can decide whether to apply. | Must | 1 | 1. The job details page must show the job description, skills, workload, and closing date. 2. The displayed details must match the stored job record. 3. The user must be able to navigate from the job list to the details view. | 2 | Epic: Job discovery | 2026-03-09 | 2026-03-22
US08 | Filter and search jobs | As a TA applicant I want to search and filter jobs So that I can find relevant positions faster. | Should | 2 | 1. The user must be able to filter jobs by at least module or skill keyword. 2. Clearing the filter must restore the full open job list. 3. If no job matches the filter, the system must show a no-results message. | 5 | Epic: Job discovery | 2026-03-23 | 2026-04-12
US09 | Apply for a job | As a TA applicant I want to apply for a job So that I can be considered for the role. | Must | 2 | 1. A logged-in applicant must be able to submit an application for an open job. 2. A successful application must be stored in the application data file. 3. A new application must start with the status Submitted. | 5 | Epic: Application flow | 2026-03-23 | 2026-04-12
US10 | Block duplicate applications | As the system I want to block duplicate applications So that application data remains valid. | Should | 2 | 1. The same applicant must not be able to submit a second application for the same job. 2. The user must be told why the application was rejected. 3. The system must keep the original valid application unchanged. | 2 | Epic: Application flow | 2026-03-23 | 2026-04-12
US11 | View application status | As a TA applicant I want to view the status of my applications So that I know the progress of each application. | Must | 2 | 1. The applicant must be able to see each submitted application. 2. The status must update correctly when an MO changes the decision. 3. The system must display statuses such as Submitted, Rejected, and Accepted clearly. | 3 | Epic: Application flow | 2026-03-23 | 2026-04-12
US12 | Withdraw a pending application | As a TA applicant I want to withdraw an unprocessed application So that I can correct or change my decision. | Should | 3 | 1. The applicant must be able to withdraw an application only while it is still pending. 2. A withdrawn application must no longer appear as active to the MO. 3. The system must show the updated withdrawn state to the applicant. | 3 | Epic: Application flow | 2026-04-13 | 2026-05-03
US13 | Post a job | As a Module Organiser I want to post a TA job So that applicants can apply for it. | Must | 2 | 1. The MO must be able to enter the core job fields and save the job. 2. Required job fields must be validated before saving. 3. A published job must appear in the applicant job list. | 5 | Epic: MO recruitment | 2026-03-23 | 2026-04-12
US14 | Edit or close a job | As a Module Organiser I want to edit or close a job So that the job list remains accurate. | Should | 3 | 1. The MO must be able to update job details before the post is closed. 2. A closed job must no longer accept new applications. 3. The updated status must be reflected in the job list and job details. | 3 | Epic: MO recruitment | 2026-04-13 | 2026-05-03
US15 | View applicants for a job | As a Module Organiser I want to view the applicants for my job So that I can review the candidate pool. | Must | 2 | 1. The MO must be able to open a list of applicants for a selected job. 2. The list must show core information such as applicant name and current application status. 3. The MO must only see applications related to that MO's jobs. | 3 | Epic: MO recruitment | 2026-03-23 | 2026-04-12
US16 | Review applicant details and CV | As a Module Organiser I want to review an applicant's profile and CV So that I can make a selection decision. | Must | 2 | 1. The MO must be able to open the applicant profile from the applicant list. 2. The MO must be able to access the CV reference associated with the application. 3. The displayed profile and CV reference must match the stored applicant data. | 3 | Epic: MO recruitment | 2026-03-23 | 2026-04-12
US17 | Accept or reject an applicant | As a Module Organiser I want to accept or reject an applicant So that recruitment decisions can be recorded. | Must | 2 | 1. The MO must be able to change an application from Submitted to Accepted or Rejected. 2. The decision must be saved in the application data file. 3. The applicant must see the updated decision in the application status view. | 5 | Epic: MO recruitment | 2026-03-23 | 2026-04-12
US18 | Add review notes | As a Module Organiser I want to add review notes to an application So that my reasoning is traceable. | Should | 3 | 1. The MO must be able to save notes for an application. 2. Saved notes must be visible when the application is reopened. 3. Empty or optional notes must not break the review workflow. | 2 | Epic: MO recruitment | 2026-04-13 | 2026-05-03
US19 | View TA workload dashboard | As an Admin I want to view the overall workload of TAs So that I can monitor allocation fairness. | Must | 2 | 1. The dashboard must show each TA with their accepted jobs or total workload. 2. The displayed workload must be based on accepted assignments only. 3. The admin must be able to open the dashboard without editing applicant data directly. | 5 | Epic: Workload management | 2026-03-23 | 2026-04-12
US20 | Filter workload data | As an Admin I want to filter workload data So that I can inspect specific TAs or modules quickly. | Should | 3 | 1. The admin must be able to filter workload by TA name or module. 2. Clearing the filter must restore the full workload view. 3. The system must show a clear message if no record matches the filter. | 3 | Epic: Workload management | 2026-04-13 | 2026-05-03
US21 | Highlight overload risk | As an Admin I want overload risk to be highlighted So that I can identify allocation problems early. | Should | 3 | 1. The system must identify workload above a defined threshold. 2. Records above the threshold must be highlighted clearly. 3. The rule used for overload must be documented in the system or user manual. | 3 | Epic: Workload management | 2026-04-13 | 2026-05-03
US22 | Validate input data | As a user I want invalid input to be rejected clearly So that the stored system data remains clean and reliable. | Must | 2 | 1. Required fields must not allow empty submission. 2. Invalid formats must produce a clear validation message. 3. Invalid input must not be written to the data file. | 5 | Epic: Quality and reliability | 2026-03-23 | 2026-04-12
US23 | Handle file errors gracefully | As a user I want file errors to be handled safely So that the system does not fail without explanation. | Should | 3 | 1. Missing or unreadable files must trigger a clear error message. 2. The application must fail gracefully rather than crashing silently. 3. The user must be able to continue or retry where appropriate. | 5 | Epic: Quality and reliability | 2026-04-13 | 2026-05-03
US24 | Show explainable skill match | As a Module Organiser I want to see an explainable skill match score So that shortlisting can be faster and more transparent. | Could | 4 | 1. The system must compare applicant skills against job skill requirements. 2. A score or ranking must be shown together with the reason for the result. 3. The explanation must reference visible skill tags rather than a black-box result only. | 5 | Epic: Explainable support | 2026-05-04 | 2026-05-24
US25 | Suggest missing skills | As a TA applicant I want to see which skills are missing for a job So that I know how to improve future applications. | Could | 4 | 1. The system must identify missing skills by comparing the profile to the job requirements. 2. The missing skills must be shown as a readable list. 3. The suggestion must be based on stored job requirements and applicant skills. | 3 | Epic: Explainable support | 2026-05-04 | 2026-05-24